PAVOAD UNR

March 22, 2024

* Case 547 (Linda Frey)
  + Previously approved for $4000
  + $2000 in additional funding needed because contractor did not include everything necessary to complete roof repair in original bid
    - Brian recommends utilizing the Lowe’s grant to purchase supplies; will discuss with contractor
    - $3000 deposit needed
  + Phase two will be interior work; will need to be presented again for additional funding and volunteers
  + Brian moves to utilize the Lowe’s grant not to exceed $1000 and the additional funding to be provided by LCS up to $2000. Karl seconds. All in favor, none opposed. Motion carries.
* Case in York county (Biran Baer)
  + Can Lowe’s gift cards be used to purchase fencing? Approx $600-$800
  + York county can provide volunteer labor
  + Some work already provide by SERVANTS
  + How much is left in Lowe’s gift cards?
    - Amanda will check
  + To be formally presented at next UNR meeting
* SBP
  + DART 9 and 19
  + TES – Dart 9
  + Project Restoration - Dart 19
  + Will still need funding for cases
  + 317 status – Amanda will check
* Any checks from PSEC won’t go out until Wednesday, April 3 because of Holy Week and Easter break.
* Julia Pedrosa (FEMA)
  + Transitioning to disaster survivor assistance
    - Door to door registrations right after a disaster